## Sam
| Assigned | Address | Name | Status |  | Next Step | On/Before | Last Contact/Action | Most Recent | Start Date | Occupancy | Scope Completed | Code Compliance | Closed Date | Ext Date
1 | Sam | 6090 N 38th St | Zong Yang | Escrow Balance | 2473.63 | Resolve Escrow Balance |  |  | 2017-05-22 |  |  |  |  | 2014-07-05
2 | Sam | 2016 N 24th Pl | Vue Thao | Escrow Balance | 2225.85 | Resolve Escrow Balance |  |  | 2015-05-29 |  |  |  |  | 2014-09-12
3 | Sam | 3526-28 W Highland | Johnnie Ashley | Escrow Balance | 279 | Resolve Escrow Balance |  |  | 2016-12-13 |  |  |  |  | 2016-05-06
4 | Sam | 5264A N 36th St | Walter Glover | Escrow Balance | 14100 | Resolve Escrow Balance |  |  | 2017-02-28 |  |  |  |  | 2017-01-04
5 | Sam | 3017-19 W Juneau | Tiffany Miller | Escrow Balance | 4000 | Resolve Escrow Balance |  |  | 2017-05-02 |  |  |  |  | 2017-01-04
6 | Sam | 2147 N 32nd St | Terry Brown | Escrow Balance | 7600 | Resolve Escrow Balance |  |  | 2017-03-23 |  |  |  |  | 2017-01-04
7 | Sam | 4929 N 20th St | Yolanda Richardson | Escrow Balance | 10000 | Resolve Escrow Balance |  |  | 2017-03-01 |  |  |  |  | 2017-01-24
8 | Sam | 2819-21 N 39th St | Sai Tong Cha | Code Close-Out |  | Follow up with scope Inspection and Code Comply Certification |  |  |  | 2014-05-09 | [5 empty] | 60 days | 2016-04-01 | Cleanup only
9 | Sam | 5542 N. 38th St. | See Cha | Expediting |  | Follow up with owner interior rehab status |  |  |  | 2014-06-12 | [6 empty] | 2016-04-01
10 | Sam | 4668 N. 30th St. | Kenjilee Cha | Expediting |  | finish electric and heating;inspect;install drywall |  |  |  | 2014-07-08 | [6 empty] | 2016-04-01
11 | Sam | 2044 S 25th St | Vicente Martinez | Program Close-Out |  | Andy inspection |  |  |  | 2014-07-11 | 2014-12-22 | [5 empty] | 2016-04-01
12 | Sam | 1449 n 35th st | Laura Mcdonald | Code Close-Out |  | close electric and construction permits |  |  |  | 2014-07-25 | 2015-06-01 | [5 empty] | 2016-04-01
13 | Sam | 3305 W Wells St | Angellica Lewis | Program Close-Out |  | Close out porch permit |  |  |  | 2014-07-28 | 2014-10-15 |  |  |  |  | 30 days | 2016-04-01 | Close permits
14 | Sam | 2918 N 7th Street | Morgan Torrence | Code Close-Out |  | Verify staus for ccc with Andy |  |  |  | 2014-08-28 | 2015-08-01 |  |  |  |  | 120 days | 2016-05-01 | Need siding
15 | Sam | 2235 W Galena St | Wang Chao Lee | Code Close-Out |  | Complete exterior work |  |  |  | 2014-09-12 | 2015-11-01 |  |  |  |  | 90 days | 2016-05-01 | Spiral staircase/waiting for material
16 | Sam | 2016 N 24th Pl | Vue Thao | Code Close-Out |  | Follow up with owner interior code comply and final inspection with Andrew |  |  |  | 2014-09-12 | 2014-11-17 |  |  |  |  | 90 days | 2016-05-01 | Need permit for porch
17 | Sam | 4516 N 44th Street | Sha'Juan Kennedy | Program Close-Out |  | Correct code violations on garage |  |  |  | 2014-09-30 | 2014-12-08 |  |  |  |  | 120 days | 2016-05-01 | verify with Andy
18 | Sam | 1700-02 W Meinecke Ave | Tashan Maye | Code Close-Out |  | working on interior and windows |  |  |  | 2014-10-10 | 2015-09-30 |  |  |  |  | 120 days | 2016-05-01 | windows and drywall
19 | Sam | 3532-34 n Port Washington ave | Leroy Shanks Sr | Closed |  | Ck w/Andy CCC |  |  |  | 2014-10-30 | 2015-05-30 |  |  |  |  | 120 days | 2016-05-01 | call for conversation
20 | Sam | 3221 W Lisbon Ave | Raphael Sivongsa | Expediting |  | Follow up owner plumbing design plan for permit |  |  |  | 2014-11-05 | [5 empty] | 90 days | 2016-05-01 | paint gutters and porch when weather changes
21 | Sam | 2152-54 S 16th | Maria Hernandez | Code Close-Out |  | Fininsh lower unit rehab |  |  |  | 2014-11-25 | 2015-07-24 | [5 empty] | 2016-05-01
22 | Sam | 2143/45 N 36th Street | Hassan Hassan | Code Close-Out |  | Check on CCC with Andy |  |  |  | 2014-11-28 | 2015-02-21 | 2015-03-27 |  |  |  |  | 2016-05-01
23 | Sam | 5703 N 55th Place | Jullian Nelson | Code Close-Out |  | Setup appt for code-compliance, exterior extension for painting |  |  |  | 2014-12-08 | 2015-01-01 |  |  |  |  | 120 days | 2016-06-01 | Outside work…wethare permitting
24 | Sam | 4055/57 N 9th Street | Corey Tucker | Code Close-Out |  | Check status for code-compliance |  |  |  | 2015-01-26 | 2015-04-01 |  |  |  |  | 120 days | 2016-06-01 | exterior paint
25 | Sam | 8859-M N Swan Rd | Roy Niedfeldt | Code Close-Out |  | Close permits CCC inspection with Andy |  |  |  | 2015-02-06 | [5 empty] | 120 days | 2016-06-01 | working with the county/garage
26 | Sam | 3213-A W Vliet Street | William B Smith | Code Close-Out |  | check ccc status |  |  |  | 2015-02-13 | 2015-05-06 | 2015-05-06 |  |  |  | 120 days | 2016-06-01 | help from rehab
27 | Sam | 1824/26 W Galena | Vang Hm Yang | Code Close-Out |  | Checkup on compliance plan |  |  |  | 2015-04-24 | [5 empty] | 180 Days | 2016-07-01 | Inspector granted extension
28 | Sam | 2450 n 46th st | Rhonda Allen | Program Close-Out |  | check on owners work scope or bid |  |  |  | 2015-05-22 | 2015-05-22 | [5 empty] | 2016-07-01
29 | Sam | 2322 North 9th Street | Cavin Plummer | Code Close-Out |  | Exterior work complete , Owner to do or bid interior |  |  |  | 2015-05-26 | 2015-05-05 | [5 empty] | 2016-07-01
30 | Sam | 4723 n 40th st | Angela Cole | Code Close-Out |  | Close permits Replace roof |  |  |  | 2015-05-29 | 2015-08-01 | [5 empty] | 2016-07-01
31 | Sam | 4536 N 23rd Street | Paul Grant | Closed |  | visit Buyer to review scope and assist w/City Req rehab |  |  |  | 2015-07-06 | 2015-07-15 | [5 empty] | 2016-07-01
32 | Sam | 3418 n 14th St | Stan Gilmer | Expediting |  | Secure property, Start electric upgrade |  |  |  | 2015-07-23 | [6 empty] | 2016-12-01
33 | Sam | 3347 N 13th Street | Brandon DeJohnette | Closed |  | see notes |  |  |  | 2015-08-24 | 2015-08-24 |  |  |  |  | Private HBA ? |  | Sent to court
34 | Sam | 4621 n 37th st | Clayton Malliett | Closed |  | Start rehab |  |  |  | 2015-10-02 | [5 empty] | to verify
35 | Sam | 4420 N 37th St | Anthony Smith | Code Close-Out |  | Owner to get bids for porch and electric |  |  |  | 2015-10-19 | 2015-10-19 | 2015-10-08 |  |  |  | Private |  | nothing to do
36 | Sam | 3729 N 5th Street | Christian Medina Cruz | Code Close-Out |  | work on exterior paint in spring |  |  |  | 2015-10-27 | 2015-11-15 |  |  |  |  | HBA |  | nothing to do
37 | Sam | 3299 N. 9th St | Michael D Thomas | Code Close-Out |  | Work on exterior code violations |  |  |  | 2014-12-19 | 2015-05-01 |  |  |  |  | 120 days | 2016-06-01 | Waiting to work on garage in spring

## Ramon
| Assigned | Address | Name | Status |  | Next Step | On/Before | Last Contact/Action | Most Recent | Start Date | Occupancy | Scope Completed | Code Compliance | Closed Date | Ext Date
1 | Blia Cha | 2457 N 25th St |  | Closed |  | Follow up with Blia to close deal |  |  |  | 2015-08-21 | [7 empty] | Need to be sold
2 | Hilaria Rios | 1596 S. Muskego | Itzel A. Lopez villanueva | Expediting |  | Plumbing |  |  |  | 2015-03-31 | [5 empty] | 180 days | 2016-07-01 | Slow but good work
3 | Ramon | 114 E Rosedale Ave | Homero Santos-Martinez | Escrow Balance | 1237.93 | Resolve Escrow Balance |  |  | 2015-12-23 |  |  |  |  | 2014-07-10
4 | Ramon | 2235-35A N 40th St | Chai Cha | Escrow Balance | 6918.08 | Resolve Escrow Balance |  |  | 2016-05-31 |  |  |  |  | 2014-09-26
5 | Ramon | 2347-47A S 16th St | Guillermo Valadez-Garcia | Escrow Balance | 2500 | Resolve Escrow Balance |  |  | - |  |  |  |  | 2016-02-23
6 | Ramon | 2201 S 14th St | Norma Damian (Rehab#2) | Escrow Balance | 3965.49 | Resolve Escrow Balance |  |  | 2016-10-04 |  |  |  |  | 2016-05-09
7 | Ramon | 1519 S 8th St | Anselmo Gamboa-Cazarin | Escrow Balance | 15000 | Resolve Escrow Balance |  |  | - |  |  |  |  | 2016-06-03
8 | Ramon | 2405 W Fairmont | Tonya Rich | Escrow Balance | 11477.91 | Resolve Escrow Balance |  |  | 2017-03-17 |  |  |  |  | 2016-08-31
9 | Ramon | 4661 N 29th St | Norma Mendoza | Escrow Balance | 3469.48 | Resolve Escrow Balance |  |  | 2017-04-19 |  |  |  |  | 2016-10-11
10 | Ramon | 1218 N 26th St | Fany Alanis (Rehab#2) | Escrow Balance | 6357.31 | Resolve Escrow Balance |  |  | 2017-05-31 |  |  |  |  | 2016-11-14
11 | Ramon | 1035-37 N 20th St | Ondina Andino | Escrow Balance | 20000 | Resolve Escrow Balance |  |  | - |  |  |  |  | 2016-12-06
12 | Ramon | 4619 N 45th St | Jorge Toto | Escrow Balance | 7810.16 | Resolve Escrow Balance |  |  | 2017-05-10 |  |  |  |  | 2017-01-11
13 | Ramon | 1406 S 25th St | Jose J. Guerra-Dominguez | Code Close-Out |  | Code compliance certificate |  |  |  | 2014-02-17 | 2014-11-03 | 2015-02-27 |  |  |  | 60 days | 2016-04-01 | Close permits
14 | Ramon | 1013 S Layton Blvd | Eduardo Mejia Gutierrez | Code Close-Out |  | Code compliance certificate |  |  |  | 2014-05-07 | 2014-09-16 | 2015-07-27 |  |  |  | 60 Days | 2016-04-01 | Close permits
15 | Ramon | 1310 N 19th St | Danny Sayaovang | Code Close-Out |  | Follow up with owner for electrical approval and sign off |  |  |  | 2014-05-22 | 2014-11-25 |  |  |  |  | 60 days | 2016-04-01 | verify with Andy
16 | Ramon | 1744 S Pearl St | Rocio Conzuelo Rodriguez-Ruiz | Code Close-Out |  | Code compliance Certificate |  |  |  | 2014-06-03 | 2014-10-15 | 2015-07-27 |  |  |  | 90 days | 2016-04-01 | drywall work
17 | Ramon | 1519 S 8th ST | Alicia Gamboa- Cazarin | Expediting |  | Loan request |  |  |  | 2015-02-17 | [6 empty] | 2016-06-01
18 | Ramon | 1104 S 23rd St | bianca Sanchez-Estrada | Expediting |  | Permits for general work out side, porch fence, etc. |  |  |  | 2015-04-17 | [5 empty] | 180 days | 2016-07-01 | Need more money
19 | Ramon | 1915A S Winona Lane | Jose De Jesus Huerta-Saavedra | Closed |  | Code compliance certificate |  |  |  | 2015-05-04 |  | 2015-09-16 |  |  |  | 180 days | 2016-07-01 | good work/slow
20 | Ramon | 1841 N 18th St | Chue Mai Xiong | Program Close-Out |  | Follow up code compliance |  |  |  | 2015-05-14 | [5 empty] | 180 days | 2016-07-01 | Slow but good work/ need electrical work/Sam to check
21 | Ramon | 2318 W Vine St | Jackie Cheng Lor | Expediting |  | Follow up code compliance |  |  |  | 2015-06-22 | [6 empty] | 2016-07-01
22 | Ramon | 1219-1221 W Arthur Ave | Maria Magdalena Saldana-Hernandez | Expediting |  | Electrical work |  |  |  | 2015-07-27 | [7 empty] | applying for loan
23 | Ramon | 833 W. Maple St. | Alfredo Herrera-Romero | Expediting |  | Finishing Painting texture |  |  |  | 2015-07-30 | [7 empty] | need a loan
24 | Ramon | 2125 W Brown St | Benton Thao | Closed |  | File closed |  |  |  | 2015-10-01 | [5 empty] | Private |  | Private
25 | Ramon | 1102 S 35th ST | Jose Luis Rodriguez-Nunez | Expediting |  | Inspection Plumbing |  |  |  | 2015-10-08 | [5 empty] | to verify
26 | Ramon | 1555 S 12th St 53204 | Ramon Garcia-Gallardo | Expediting |  | Electrical rough inspection |  |  |  | 2015-10-12 | [5 empty] | HBA ? |  | nothing to do